## Project tasks
Project name | Personal Tutoring Services
Project manager | Sanjana T
Project start date | 2023-09-05 09:00
Project finish date | 2023-12-05 17:00
Duration | 66 days
% complete | 44%
Exported on | 2023-10-20 01:10
Task number | Outline number | Name | Assigned to | Duration | Start | Finish | Effort | Depends on | % complete | Bucket | Dependents (after) | Effort completed | Effort remaining | Milestone | Notes | Completed | Checklist Items | Labels | Priority | Sprint | Goal
1 | 1 | Project Initiation and Requirement Gathering |  | 11 days | 2023-09-05 09:00 | 2023-09-19 17:00 | 176 hours |  | 100% |  | 7FS | 176 hours | 0 hours | No |  |  |  |  | Medium
2 | 1.1 | Initial Client Meeting | Sanjana T, anand pavan | 2 days | 2023-09-05 09:00 | 2023-09-06 17:00 | 32 hours |  | 100% | Bucket 1 | 3FS | 32 hours | 0 hours | No |  |  |  |  | Important | Backlog
3 | 1.2 | Define Project Scope and Objectives | Sanjana T, akanksha chenna | 2 days | 2023-09-07 09:00 | 2023-09-08 17:00 | 32 hours | 2FS | 100% | Bucket 1 | 4FS | 32 hours | 0 hours | No |  |  |  |  | Medium | Backlog
4 | 1.3 | Identify Key Stakeholders and Roles | Sanjana T, pooja reddy | 2 days | 2023-09-11 09:00 | 2023-09-12 17:00 | 32 hours | 3FS | 100% | Bucket 1 |  | 32 hours | 0 hours | No |  |  |  |  | Medium | Backlog
5 | 1.4 | Create Requirement Gathering Plan | Sanjana T, jeetesh pavan | 2 days | 2023-09-13 09:00 | 2023-09-14 17:00 | 32 hours |  | 100% | Bucket 1 |  | 32 hours | 0 hours | No |  |  |  |  | Medium | Backlog
6 | 1.5 | Conduct Market Analysis and Research | Sanjana T, manideep reddy | 3 days | 2023-09-15 09:00 | 2023-09-19 17:00 | 48 hours |  | 100% | Bucket 1 |  | 48 hours | 0 hours | No |  |  |  |  | Medium | Backlog
7 | 2 | Architecture and Design |  | 11 days | 2023-09-20 09:00 | 2023-10-04 17:00 | 320 hours | 1FS | 100% |  | 14FS | 320 hours | 0 hours | No |  |  |  |  | Medium
8 | 2.1 | Develop System Architecture | manideep reddy, akanksha chenna | 3 days | 2023-09-20 09:00 | 2023-09-22 17:00 | 48 hours |  | 100% | Bucket 1 | 9FS, 13FS | 48 hours | 0 hours | No |  |  |  |  | Medium | Backlog
9 | 2.2 | Design User Interface (UI) Wireframes | manideep reddy, Sanjana T | 3 days | 2023-09-25 09:00 | 2023-09-27 17:00 | 48 hours | 8FS | 100% | Bucket 1 |  | 48 hours | 0 hours | No |  |  |  |  | Medium | Backlog
10 | 2.3 | Develop Database Structure | akanksha chenna, manideep reddy | 2 days | 2023-09-28 09:00 | 2023-09-29 17:00 | 32 hours |  | 100% | Bucket 1 |  | 32 hours | 0 hours | No |  |  |  |  | Medium | Backlog
11 | 2.4 | Identify and select the appropriate technology stack | anand pavan, pooja reddy | 2 days | 2023-10-02 09:00 | 2023-10-03 17:00 | 32 hours |  | 100% | Bucket 1 |  | 32 hours | 0 hours | No |  |  |  |  | Medium | Backlog
12 | 2.5 | Ensure Security Protocols | jeetesh pavan, akanksha chenna | 2 days | 2023-10-03 09:00 | 2023-10-04 17:00 | 32 hours |  | 100% | Bucket 1 |  | 32 hours | 0 hours | No |  |  |  |  | Medium | Backlog
13 | 2.6 | Conduct Architecture Review Meetings | Sanjana T, anand pavan | 8 days | 2023-09-25 09:00 | 2023-10-04 17:00 | 128 hours | 8FS | 100% | Bucket 1 |  | 128 hours | 0 hours | No |  |  |  |  | Medium | Backlog
14 | 3 | Development Phase |  | 22 days | 2023-10-05 09:00 | 2023-11-03 17:00 | 520 hours | 7FS | 30% |  |  | 192 hours | 328 hours | No |  |  |  |  | Medium
15 | 3.1 | Frontend Development |  | 7 days | 2023-10-05 09:00 | 2023-10-13 17:00 | 112 hours |  | 100% |  | 21FS, 22FS, 23FS | 112 hours | 0 hours | No |  |  |  |  | Medium
16 | 3.1.1 | Develop the user interface | pooja reddy, akanksha chenna | 5 days | 2023-10-05 09:00 | 2023-10-11 17:00 | 80 hours |  | 100% | Bucket 1 |  | 80 hours | 0 hours | No |  |  |  |  | Medium | Backlog
17 | 3.1.2 | Implement the registration and login/authentication | anand pavan, akanksha chenna | 2 days | 2023-10-12 09:00 | 2023-10-13 17:00 | 32 hours |  | 100% | Bucket 1 |  | 32 hours | 0 hours | No |  |  |  |  | Medium | Backlog
18 | 3.2 | Backend Development |  | 8 days | 2023-10-16 09:00 | 2023-10-25 17:00 | 128 hours |  | 63% |  | 21FS, 22FS, 23FS | 80 hours | 48 hours | No |  |  |  |  | Medium
19 | 3.2.1 | Build the backend infrastructure for user data storage and session management | anand pavan, jeetesh pavan | 5 days | 2023-10-16 09:00 | 2023-10-20 17:00 | 80 hours |  | 100% | Bucket 1 |  | 80 hours | 0 hours | No |  |  |  |  | Medium | Backlog
20 | 3.2.2 | Implement the functionality for tutoring categories and addition of new categories | Sanjana T, manideep reddy | 3 days | 2023-10-23 09:00 | 2023-10-25 17:00 | 48 hours |  | 0% | Bucket 1 |  | 0 hours | 48 hours | No |  |  |  |  | Medium | Backlog
21 | 3.3 | Payment Integration | pooja reddy, jeetesh pavan | 2 days | 2023-10-26 09:00 | 2023-10-27 17:00 | 32 hours | 15FS, 18FS | 0% | Bucket 1 |  | 0 hours | 32 hours | No |  |  |  |  | Medium | Backlog
22 | 3.4 | Communication Setup | manideep reddy, anand pavan | 3 days | 2023-10-30 09:00 | 2023-11-01 17:00 | 48 hours | 15FS, 18FS | 0% | Bucket 1 |  | 0 hours | 48 hours | No |  |  |  |  | Medium | Backlog
23 | 3.5 | Search and Review Functionality | pooja reddy, manideep reddy | 2 days | 2023-11-02 09:00 | 2023-11-03 17:00 | 32 hours | 15FS, 18FS | 0% | Bucket 1 |  | 0 hours | 32 hours | No |  |  |  |  | Medium | Backlog
24 | 3.6 | Monitoring and Control System | jeetesh pavan | 15 days | 2023-10-16 09:00 | 2023-11-03 17:00 | 120 hours |  | 0% | Bucket 1 |  | 0 hours | 120 hours | No |  |  |  |  | Medium | Backlog
25 | 3.7 | Map Integration and Advertisement Setup | pooja reddy, manideep reddy | 3 days | 2023-11-01 09:00 | 2023-11-03 17:00 | 48 hours |  | 0% | Bucket 1 |  | 0 hours | 48 hours | No |  |  |  |  | Medium | Backlog
26 | 4 | Mobile App Development |  | 23 days | 2023-10-18 09:00 | 2023-11-17 17:00 | 312 hours |  | 22% |  |  | 80 hours | 232 hours | No |  |  |  |  | Medium
27 | 4.1 | Android Application Interface Design | manideep reddy, akanksha chenna | 5 days | 2023-10-18 09:00 | 2023-10-24 17:00 | 80 hours |  | 100% | Bucket 1 | 28FS | 80 hours | 0 hours | No |  |  |  |  | Medium | Backlog
28 | 4.2 | Feature Implementation | pooja reddy | 7 days | 2023-10-25 09:00 | 2023-11-02 17:00 | 56 hours | 27FS | 0% | Bucket 1 | 29FS | 0 hours | 56 hours | No |  |  |  |  | Medium | Backlog
29 | 4.3 | Integration with Backend Systems | anand pavan, pooja reddy | 4 days | 2023-11-03 09:00 | 2023-11-08 17:00 | 64 hours | 28FS | 0% | Bucket 1 | 30FS | 0 hours | 64 hours | No |  |  |  |  | Medium | Backlog
30 | 4.4 | Testing the compatibility of Android application | akanksha chenna, pooja reddy | 4 days | 2023-11-09 09:00 | 2023-11-14 17:00 | 64 hours | 29FS | 0% | Bucket 1 | 31FS | 0 hours | 64 hours | No |  |  |  |  | Medium | Backlog
31 | 4.5 | Performance Optimization | manideep reddy, jeetesh pavan | 3 days | 2023-11-15 09:00 | 2023-11-17 17:00 | 48 hours | 30FS | 0% | Bucket 1 |  | 0 hours | 48 hours | No |  |  |  |  | Medium | Backlog
32 | 5 | Testing, Feedback, Deployment, Review |  | 14 days | 2023-11-16 09:00 | 2023-12-05 17:00 | 216 hours |  | 0% |  |  | 0 hours | 216 hours | No |  |  |  |  | Medium
33 | 5.1 | Comprehensive Testing | akanksha chenna | 5 days | 2023-11-16 09:00 | 2023-11-22 17:00 | 40 hours |  | 0% | Bucket 1 | 34FS | 0 hours | 40 hours | No |  |  |  |  | Medium | Backlog
34 | 5.2 | User Feedback Collection | Sanjana T, akanksha chenna | 2 days | 2023-11-23 09:00 | 2023-11-24 17:00 | 32 hours | 33FS | 0% | Bucket 1 | 35FS | 0 hours | 32 hours | No |  |  |  |  | Medium | Backlog
35 | 5.3 | Iterative Improvements | Sanjana T, jeetesh pavan | 4 days | 2023-11-27 09:00 | 2023-11-30 17:00 | 64 hours | 34FS | 0% | Bucket 1 | 36FS | 0 hours | 64 hours | No |  |  |  |  | Medium | Backlog
36 | 5.4 | Final Quality Assurance | akanksha chenna, Sanjana T | 1 day | 2023-12-01 09:00 | 2023-12-01 17:00 | 16 hours | 35FS | 0% | Bucket 1 | 38FS | 0 hours | 16 hours | No |  |  |  |  | Medium | Backlog
37 | 5.5 | Documentation Preparation | Sanjana T, manideep reddy | 2 days | 2023-12-01 09:00 | 2023-12-04 17:00 | 32 hours |  | 0% | Bucket 1 |  | 0 hours | 32 hours | No |  |  |  |  | Medium | Backlog
38 | 5.6 | Deployment | Sanjana T, pooja reddy | 1 day | 2023-12-04 09:00 | 2023-12-04 17:00 | 16 hours | 36FS | 0% | Bucket 1 | 39FS | 0 hours | 16 hours | No |  |  |  |  | Medium | Backlog
39 | 5.7 | Final Review | Sanjana T, anand pavan | 1 day | 2023-12-05 09:00 | 2023-12-05 17:00 | 16 hours | 38FS | 0% | Bucket 1 |  | 0 hours | 16 hours | No |  |  |  |  | Medium | Backlog

## Resources
RESOURCE | GROUP | TYPE | HOURS ASSIGNED | COST$/HR | TOTAL COST
SANJANA REDDY | Project manager | HUMAN R | 576 | 100 | 57600
POOJA REDDY | Sr. Developer | HUMAN R | 456 | 50 | 22800
ANAND PAVAN | Sr. Developer | HUMAN R | 432 | 50 | 21600
MANIDEEP | System Architect | HUMAN R | 512 | 50 | 25600
AKANKSHA | Developer | HUMAN R | 488 | 50 | 24400
JEETESH | Software tester | HUMAN R | 408 | 50 | 20400
W |  | Material R
X |  | Material R
Y |  | Material R
Z |  | Material R
TOTAL COST |  |  |  |  | 172400